## Sheet1
ID | Feature Name | Description | Priority | Status | MVP | Category | Epic ID | Epic | Story ID | User Story | Persona
ARC-001 | Research-First Content Generation | Enforced constraint: 'New Idea' button is disabled until ≥1 research source is selected from the Research Results drawer. Gate logic in StrategyResearch prevents idea creation without source context. | P0 | Completed | MVP | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
ARC-002 | AI Research Runner | One-click 'Run Research' in StrategyResearch triggers AI source scanning with loading spinner. Results appear in an expandable drawer below the research bar. Mock AI results seeded from wellness/Hive Collective data. | P0 | Completed | MVP | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
ARC-003 | Research Source Cards | Source cards in StrategyResearch showing: pillar badge, title, expandable summary, external URL link, selection checkbox, and bookmark toggle. Responsive 1–3 column grid with scrollable results area. | P0 | Completed | MVP | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
ARC-004 | Source-to-Idea Conversion | Selected research sources converted to content ideas via 'Create Ideas' action. Auto-populates title, pillar, description (from summary), source URL, and sets stage to 'Idea'. Batch creation supported with toast feedback. | P0 | Completed | MVP | AI Research & Content Engine | EP-03 | Content Creation & AI | US-06 | Turn research into content ideas | Content Creator
ARC-005 | Research Library | Persistent Library tab in StrategyResearch for saved/bookmarked sources. Sources saved when bookmarked or used to create ideas. Manual deletion with toast undo. Persists to localStorage. | P1 | Completed |  | AI Research & Content Engine | EP-02 | AI Research Engine | US-06 | Turn research into content ideas | Content Creator
ARC-006 | Research Pillar Filtering | Pillar dropdown filter in StrategyResearch filters displayed research results to a specific content pillar. 'All Pillars' option resets filter. Works on both AI results and library. | P1 | Completed |  | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
ARC-007 | Manual Source Addition | Add custom research sources to the library via dialog form: title (required), URL, summary text, and pillar assignment. Validates that title and at least one of URL or summary are provided. | P1 | Completed |  | AI Research & Content Engine | EP-03 | Content Creation & AI | US-06 | Turn research into content ideas | Content Creator
ARC-008 | AI Script Generation | Generate short-form video scripts from content ideas in ContentProduction Draft tab. Output includes hook, narrative body, and CTA. Simulated AI generation with loading state; generated content stored with timestamp. | P1 | Completed |  | AI Research & Content Engine | EP-03 | Content Creation & AI | US-06 | Turn research into content ideas | Content Creator
ARC-009 | AI Asset Generation Pipeline | Assets tab in ContentProduction manages required asset checklist (video clips, thumbnails, graphics) with completion tracking. AI generation simulation for thumbnails and clips. Full real-AI pipeline and file upload integration pending. | P2 | In Progress |  | AI Research & Content Engine | EP-03 | Content Creation & AI | US-06 | Turn research into content ideas | Content Creator
ARC-010 | Research Source Scoring & Ranking | AI-powered relevance scoring for discovered sources based on workspace pillars, audience alignment, and recency. Auto-sort by relevance score. | P2 | Not Started |  | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
ARC-011 | RSS Feed Integration | Connect RSS feeds as persistent research sources. Agents automatically scan feeds on schedule and surface new articles matching content pillars. | P2 | Not Started |  | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
ARC-012 | Research Source Deduplication | Detect and flag or auto-merge duplicate research sources across manual additions and AI-discovered results to keep the library clean. | P2 | Not Started |  | AI Research & Content Engine | EP-02 | AI Research Engine | US-05 | Find relevant research sources with AI | Content Creator
IDP-001 | Workspace Settings Dashboard | WorkspaceSettings component with 7 tabs: General (name, brand voice, branding), Platforms (per-platform accordion with full specs), Content (pillars + audience segments CRUD), Agents (AI agent team editor), Team (member management), Notifications (channel + trigger toggles), Security (2FA, sessions, API keys). Active tab highlighted with #d94e33 accent. | P0 | Completed | MVP | Identity & Personalization | EP-06 | Workspace Configuration | US-13 | Configure workspace identity and branding | Workspace Admin
IDP-002 | User Profile Management | ProfileSettings page: Display Name, Email, avatar, Current Workspace Role (Admin shield badge), Workspace Access count, linked accounts section, and danger zone. Password change sub-section with current/new/confirm fields and 8-char minimum validation inline. | P0 | Completed | MVP | Identity & Personalization | EP-07 | Team & Security | US-12 | Manage my account and security | User
IDP-003 | Brand Voice Configuration | Brand voice textarea in WorkspaceSettings General tab. Defines tone/style for AI content generation. Saved to localStorage and referenced during AI generation prompts. Editable at any time post-setup. | P1 | Completed |  | Identity & Personalization | EP-06 | Workspace Configuration | US-03 | Define my content strategy | Content Strategist
IDP-004 | Agent Bio & Behavior Editor | WorkspaceSettings Agents tab: inline edit toggle per agent (name, role, bio, responsibilities, desired outputs), archive action, add new agent form, and remove agent with confirmation. Animated list transitions for add/remove. | P1 | Completed |  | Identity & Personalization | EP-03 | Content Creation & AI | US-10 | Customize my AI agent team | Workspace Admin
IDP-005 | Team Management | WorkspaceSettings Team tab: current members list with name, role badge, email, and 'me' indicator. Invite new member via email input + role select. Remove member with confirmation. Role options: Admin, Editor, Viewer. | P1 | Completed |  | Identity & Personalization | EP-07 | Team & Security | US-11 | Manage my team and access control | Team Lead
IDP-006 | Platform-Specific AI Styling | WorkspaceSettings Platforms tab has an accordion per active platform. Each section includes video specs, posting schedule, peak time config, AI content style dropdown, and design prompt suffix input for per-platform AI customization. | P1 | Completed |  | Identity & Personalization | EP-08 | Platform Optimization | US-02 | Configure platform-specific rules | Workspace Admin
IDP-007 | Content Pillar Management (Settings) | WorkspaceSettings Content tab + PillarsSegments component: full CRUD for content pillars (name, description, themes, audience segment mapping, platform distribution) and audience segments. Changes sync to StrategyResearch pillar filter and ContentIdeas pillar selectors. | P1 | Completed |  | Identity & Personalization | EP-06 | Workspace Configuration | US-03 | Define my content strategy | Content Strategist
IDP-008 | Password Management | Password change section in ProfileSettings: current password, new password (min 8 chars with strength indicator), confirm password with match validation. Lock icon field decoration and inline error messages. | P2 | Completed |  | Identity & Personalization | EP-07 | Team & Security | US-12 | Manage my account and security | User
IDP-009 | Notification Preferences | WorkspaceSettings Notifications tab: toggle switches for email, in-app, and Slack channels. Trigger toggles for new research results, content published, team mentions, QA review required, and approaching deadlines. Per-workspace rules saved to localStorage. | P2 | Completed |  | Identity & Personalization | EP-07 | Team & Security | US-12 | Manage my account and security | User
IDP-010 | Security Settings | WorkspaceSettings Security tab: 2FA toggle (UI only), active sessions table (device/browser/location/last-active/revoke), API key display with copy, and login history. Real 2FA enrollment flow and backend session management not yet implemented. | P2 | In Progress |  | Identity & Personalization | EP-07 | Team & Security | US-12 | Manage my account and security | User
IDP-011 | Role-Based Access Control | Granular permission enforcement based on user role. Admins: full access. Editors: content management only. Viewers: read-only. Role assignment UI exists in Team tab but enforcement logic (route guards, action gating) not yet implemented. | P2 | Not Started |  | Identity & Personalization | EP-07 | Team & Security | US-11 | Manage my team and access control | Team Lead
IDP-012 | Workspace Branding & Theming | WorkspaceSettings General tab has brand color input and logo placeholder. Brand color (#d94e33) applied globally to header, nav active states, and buttons. Custom logo upload and live theme switching across all surfaces not yet implemented. | P2 | In Progress |  | Identity & Personalization | EP-06 | Workspace Configuration | US-13 | Configure workspace identity and branding | Workspace Admin
OWS-001 | 5-Step Setup Wizard | Guided workspace initialization flow with sequential steps: Workspace Identity → Platform Config → Content Strategy → Agent Team → Review & Launch. StepIndicator, AnimatePresence transitions, auto-save to localStorage, and Back/Next/Finish controls in Card footer. | P0 | Completed | MVP | Onboarding & Workspace Setup | EP-01 | Workspace Onboarding | US-01 | Set up a new workspace quickly | New User
OWS-002 | Workspace Identity Configuration | Step 1 of setup wizard (StepWorkspaceBasics). Captures workspace name, purpose statement, mission, brand voice textarea, and audience segment targets with age range selectors. | P0 | Completed | MVP | Onboarding & Workspace Setup | EP-01 | Workspace Onboarding | US-01 | Set up a new workspace quickly | New User
OWS-003 | Platform Configuration & Rules | Step 2 of setup wizard (StepPlatformConfig). Per-platform toggles for Instagram, TikTok, YouTube, LinkedIn, Facebook. Configure aspect ratio, video/thumbnail resolution, posting frequency, timezone, peak times, AI content style, and design prompt suffix. | P0 | Completed | MVP | Onboarding & Workspace Setup | EP-08 | Platform Optimization | US-02 | Configure platform-specific rules | Workspace Admin
OWS-004 | Content Pillar Definition | Step 3 of setup wizard (StepContent). Create content pillars with name, description, themes (tag input), audience segment multi-select, and platform distribution multi-select. Add/remove pillar operations with animated transitions. | P0 | Completed | MVP | Onboarding & Workspace Setup | EP-01 | Workspace Onboarding | US-03 | Define my content strategy | Content Strategist
OWS-005 | AI Agent Team Setup | Step 4 of setup wizard (StepAgents). Define AI agent personalities with name, role description, core responsibilities, and desired outputs. Animated add/remove. Pre-populated with Hive Collective example agents. | P0 | Completed | MVP | Onboarding & Workspace Setup | EP-03 | Content Creation & AI | US-10 | Customize my AI agent team | Workspace Admin
OWS-006 | Setup Review & Launch | Step 5 of setup wizard (StepReview). Summary of all configuration sections before launch. 'Finish & Launch' button transitions to the dashboard and sets activeTab to 'content'. | P0 | Completed | MVP | Onboarding & Workspace Setup | EP-01 | Workspace Onboarding | US-01 | Set up a new workspace quickly | New User
OWS-007 | Multi-Workspace Support | Home screen (Home component) with workspace tiles for Hive Collective and Booze Kills. Each tile shows branded header, quick-access links to Content/Calendar/Strategy/Performance tabs, and workspace metadata. 'New Workspace' tile triggers setup wizard. | P1 | Completed |  | Onboarding & Workspace Setup | EP-06 | Workspace Configuration | US-04 | Manage multiple brands | Power User
OWS-008 | Audience Segment Targeting | Demographic audience segments with description and age range. Defined in StepWorkspaceBasics and editable in WorkspaceSettings Content tab. Used for audience-to-pillar mapping throughout the app. | P1 | Completed |  | Onboarding & Workspace Setup | EP-01 | Workspace Onboarding | US-03 | Define my content strategy | Content Strategist
OWS-009 | Global Platform Rules | Workspace-level platform defaults in WorkspaceSettings Platforms tab: default platform, max AI ideas per month, content warning toggle, AI disclaimer auto-include. UI complete; backend persistence pending. | P1 | In Progress |  | Onboarding & Workspace Setup | EP-08 | Platform Optimization | US-02 | Configure platform-specific rules | Workspace Admin
OWS-010 | Workspace Templates | Pre-built workspace configurations for common use cases (e.g., 'B2B SaaS', 'Creator Economy', 'Agency Multi-Client') to accelerate onboarding. | P2 | Not Started |  | Onboarding & Workspace Setup | EP-06 | Workspace Configuration | US-04 | Manage multiple brands | Power User
OWS-011 | Onboarding Progress Persistence | Wizard progress persists to localStorage so users can leave and resume setup. UI shows 'Progress is automatically saved'. Cross-device sync and backend persistence not yet implemented. | P2 | In Progress |  | Onboarding & Workspace Setup | EP-01 | Workspace Onboarding | US-01 | Set up a new workspace quickly | New User
OWS-012 | Workspace Cloning | Clone an existing workspace configuration to create a new workspace with identical pillars, agents, and platform settings as a starting point. | P2 | Not Started |  | Onboarding & Workspace Setup | EP-06 | Workspace Configuration | US-04 | Manage multiple brands | Power User
WFM-001 | Content Pipeline (Kanban Board) | 5-column visual kanban in ContentPipeline: Idea → In Production → Ready to Publish → Scheduled → Published. Cards show platform icon, content type badge, pillar badge, title, and quick-open button. Multi-select filter by platform and content type. Column event counts in badges. | P0 | Completed | MVP | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-002 | Content Status System | Unified status model across all app surfaces: Draft (gray), In Progress (blue), Review (purple), Scheduled (pink), Published (green). STATUS_CONFIG drives color-coded badges, pipeline column assignments, calendar event pills, and filter chips everywhere. | P0 | Completed | MVP | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-003 | Content Ideas Views (Table / Kanban / Grid) | PipelineView component inside ContentIdeas offers three switchable layouts: Kanban (column cards), Table (sortable rows with Title, Pillar, Platform, Status, Type, Date), and Grid (card tiles). Full-text search plus filter dropdowns for Status, Pillar, Platform, Stage, and Content Type. | P0 | Completed | MVP | Workflow & Management | EP-04 | Production Pipeline | US-08 | Manage and find my content | Content Manager
WFM-004 | Content Detail View | ContentDetail component showing full idea metadata: hook, description, source URL link, target platforms (icons), content type, pillar, owner, scheduled date, and generated assets list. 'Open Production' action routes to ContentProduction with the correct starting tab. | P1 | Completed |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-005 | 6-Tab Content Production Pipeline | ContentProduction component with tabs: Brief (objective, target audience, key messages, hooks), Draft (AI script generation, rich text editor), Blueprint (shot list, b-roll notes, storyboard), Assets (required asset checklist with completion tracking and progress bar), Packaging (thumbnail config, title, description, tags, CTA, platform metadata), QA (approval checklist, reviewer sign-off, final notes). Each tab has save actions with toast feedback. Activity slide-over drawer accessible from all tabs. | P1 | Completed |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-006 | Content Calendar — Full Planning Surface | ContentCalendar component with Month, Week, Day, and List views. Features: EventPill (publish/milestone) and PhaseWindowBar (production/review spanning bars) with severity badges (overdue/at-risk/blocked). Upcoming panel (14-day lookahead with 4-priority bucket ordering). AI Insights sidebar card. Compact Popover filter with multi-select chips for Platform, Status, Event Types, and Saved Views. Active filter chip strip. Date navigation per view. Quick-add on empty day click. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-007 | Pipeline Analytics Dashboard | ContentPipeline header area shows content counts by status, platform breakdown, and content type distribution. Filters for platform (multi-select) and content type (multi-select) update all counts and card lists in real time. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-008 | Content Search & Sort | Full-text search across idea titles, pillars, and descriptions. Sort by Created Date, Title, Status, or Platform with ascending/descending toggle. Filters for Status (multi), Pillar (multi), Platform (multi), Stage, and Content Type in PipelineView and ContentIdeas header. | P1 | Completed |  | Workflow & Management | EP-04 | Production Pipeline | US-08 | Manage and find my content | Content Manager
WFM-009 | Drag-and-Drop Pipeline Cards | Drag content cards between kanban columns to update status in ContentPipeline. Visual grab/grabbing cursor feedback. react-dnd integration planned but not yet implemented. | P2 | Not Started |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-010 | Content Scheduling Engine | Publish events scheduled via Quick Edit modal on the Calendar. Date/time picker validates against past-date scheduling. Phase window start/end date editing with end-before-start validation. Review window warns when end exceeds publish date. Workspace deadline auto-apply toggle for milestone generation. | P2 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-011 | Bulk Actions on Content | Multi-select content ideas for batch operations: bulk status change, bulk delete, bulk platform assignment, and bulk pillar re-categorization. | P2 | Not Started |  | Workflow & Management | EP-04 | Production Pipeline | US-08 | Manage and find my content | Content Manager
WFM-012 | Pipeline Board Reset | One-click 'Reset Pipeline' action to clear all content cards from the kanban board for testing or fresh-start scenarios. | P2 | Not Started |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-013 | Calendar AI Insights Panel | Collapsible AI Insights card at the top of the Calendar sidebar. Dynamically computes up to 8 insight types from live event data: overdue milestones (error), blocked items with QA failures (error), at-risk publishes missing assets (warning), content gaps in next 7 days (warning), overloaded publish days 3+ same day (info), items in production without a publish date (info), platform diversity gaps — unused platforms in 30-day window (tip), review windows extending past publish date (tip). Header color shifts red/amber/violet based on severity. Insight count badge and expand/collapse toggle. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-014 | Calendar Multi-select Filter Popover | Filters button opens a Radix Popover (w-80) with: Search input, Event Types (toggle chips: Phases/Milestones/Published, default all-on), Platform (multi-select chips with icons — empty = all), Status (multi-select chips with status colors — empty = all), Saved View dropdown (7 presets), Clear all + Done footer. Active filter count badge turns button red. Applied filters shown as removable chip strip below toolbar with per-chip ✕ and 'Clear all' text link. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-08 | Manage and find my content | Content Manager
WFM-015 | Calendar Event Quick Peek Cards | Radix Popover hover card on EventPill and PhaseWindowBar (Month/Week views only; Day/List/Upcoming use Quick Edit directly). 300ms mouseenter delay, 200ms mouseleave grace. Card shows: clickable title, status/platform/type/milestone/phase chips, event summary line, active phase banner, severity banner with contextual message, up to 2 blocker snippets, owner + production step, Edit Dates/Open Item primary actions, Copy Link/Pipeline ghost actions, and routing hint. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-016 | Calendar Phase Windows & Milestone Events | Phase windows render as multi-day spanning bars: Production (blue-200 fill, blue-500 left border, Wrench icon) and Review (purple-200 fill, purple-500 left border, ClipboardCheck icon). Active phase shows ring. Auto-generated from scheduled dates (production = publish−7d to −3d, review = −2d to −1d). Milestone pills (Brief/Draft/Assets/QA Due etc.) render as dashed-border Flag pills. Severity derived from deadline proximity, asset completion, and QA approval state. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-017 | Calendar Cross-tab Deep-link Navigation | Event routing maps calendar events to the correct ContentProduction tab: milestone events use MILESTONE_TAB_MAP, phase windows use PHASE_TAB_MAP, blocked severity always routes to QA, publish events use STATUS_TAB_MAP. Double-click or 'Open Item' sets calendarOpenItem in App.tsx, switches activeTab to 'content', and ContentIdeas opens with selectedItemId + activeStep pre-set. | P1 | Completed |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-018 | Calendar Right-click Context Menus | Right-click on any EventPill or PhaseWindowBar opens a Radix ContextMenu via EventContextWrapper. Items: Open Item, Edit Dates, separator, Copy Link (writes deep-link URL to clipboard with toast), View Activity, separator, View in Pipeline. Applies to all event types across all calendar views. | P2 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-019 | Calendar Drag-and-drop Rescheduling | Drag EventPills to new dates on the calendar grid to reschedule publish/milestone events. Resize handles on PhaseWindowBar ends to extend or shrink phase windows. Drop validation: no past-date publish, end > start for phases, warning when review window extends past publish. Not yet implemented. | P2 | Not Started |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner
WFM-020 | Content Studio Overview Dashboard | ContentStudioOverview landing page for the Content tab: workspace health metrics (content by status with color-coded counts), recent activity feed, active production items list, platform distribution, pillar coverage, and quick-action buttons (New Idea, Run Research, View Calendar). Navigates to sub-sections via ContentIdeas state callbacks. | P1 | Completed |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-021 | Content Production Activity Drawer | Persistent slide-over Activity drawer accessible from all ContentProduction tabs via an Activity button in the tab header. Shows chronological event log: status transitions, file uploads, comments, QA approvals, AI generation events. Each entry has timestamp, actor, event type icon, and description. Slides in from the right without obscuring tab content. | P1 | Completed |  | Workflow & Management | EP-04 | Production Pipeline | US-07 | Track content through production | Content Manager
WFM-022 | Performance Tracking Dashboard | PerformanceTracking component (PerformanceTab) showing: KPI summary cards (views, engagement rate, reach, conversions), platform breakdown charts, top-performing content ranked list, pillar performance comparison, trend lines over time, and audience growth metrics. Fed from live content items and pillar config via localStorage. | P1 | Completed |  | Workflow & Management | EP-05 | Publishing & Scheduling | US-09 | Plan my publishing schedule | Content Planner